## Sheet1
Sr. No | User Role | Feature | Client Comment | Time Estimate | Delivery Date
1 | Customer Support Executive | Login to the application via login details created by Super admin/ sales admin |  |  | 2019-07-14
|  | Setting up the profile (i.e. completing his/ her profile details) |  | 3 hours
|  | Ability to view the sales lead shared by Franchise executive |  | 1 hours
|  | Adding all the sales lead to the system. |  | 8 hours
|  | Managing the sales lead status. |  | 2 hours
Order details a) Adding a new order b) Updating the order c) Soft deleting of the order (active/deactivate)
|  | Defining of the payment Milestones |  | 8 hours
Initial payment deposit (via payment gatway thru the system)
|  | Reports a) Order reports status b) Sales Statics (filters - days/ months/ years) |  | 8 hours
|  | Notification a) When ever there is an update in payment b) Status update c) Announcement message from admin is received. d) A lead is shared by the franchise executive |  | 3 hours
|  | Settings |  |  | 2019-07-07
2 | Franchise Executive | Login to the application via login details created by Super admin/Customer Support Admin
Setting up the profile (i.e. completing his/ her profile details)
Viewing the CV requests/ sales lead request shared by customer support admin.
Ability to assign the sales lead to customer support executive of the particular loaction.
Ability to post a job
|  | Reports a) Cv's received status b) Cv's Statics (filters - days/ months/ years) like how many CV's shared with respect to particular filtered. c) Sales lead received status d) Action take with respect to each sales lead |  | 8 hours | 2019-07-19
|  | Notification a) when ever a new Cv is received b) Announcement message from admin is received. |  | 3 hours
Settings
3 | End user | Ability to view the complete front end of the website.
|  | Submit the CV or any service request via form on the website |  | 8 hour
Contact us form (which will be directly submitted to the Admin)
4 | Customer Support Admin | Login to the application via login details created by Super admin
Ability to create logins for other users (Franchise Executive and Customer Support Executive) of the application.
|  | View Sales report w.r.t user/ location/ time period |  | 8 hours | 2019-06-28
View Cv's request w.r.t user/ location/ time period
Ability to create the customer support executive profile.
|  | Ability to assign a sales lead/Job request (Cv received) to the particular franchise Executive w.r.t location |  | 3 hours
5 | Super- Admin | User management
|  | Ability to create logins for other users of the application |  | 48 hours | 2019-06-26
View user w.r.t location
View sales report w.r.t filters user/location/time period
Access to complete master data of the application.
View messages received from the contact form and assigning it to a particular department if required.
Settings
Change Requirement
|  | Form Builder/create 12 indivisible form of according to service |  | 32 hours
|  | Show All forms of service/edit/update/ |  | 12 hours
|  | manage of all payment paid /pending of according to service |  | 10 hours
|  | recurring payment according to all user and service |  | 15 hours
|  | Dashboard ending payment for client/sale exective/superadmin/franchise |  | 8 hours