## Sheet1
Sr. No | User Role | Feature | Client Comment | Time Estimate | Delivery Date
1 | Customer Support Executive | Login to the application via login details created by Super admin/ sales admin | ok |  | 2019-07-14
|  | Setting up the profile (i.e. completing his/ her profile details) | It's not giving me options to write the name of the CSA or gender. Please add a unique employee number of each person in the company starting from P001 as the Super Admin |  |  | On the Dashboard for (CSE) only have completed sales, Pending Sales, Team Member and a message portal.
|  | Ability to view the sales lead shared by Franchise executive | All user must have First Name, Surname, Date of Birth, Gender and ID |  |  | Change the Sales service to (Place Order)
|  | Adding all the sales lead to the system. |  |  |  | Insted of View sales have (Completed Sales, Order placed and Pending Order)
|  | Managing the sales lead status. |  | I tried to complete an order but the order didn't complete and it has created a new user with the email address which i entered on the order form. i guess you'll change that. |  | Order form use pound sign not doller sign
|  | Order details a) Adding a new order b) Updating the order c) Soft deleting of the order (active/deactivate) |  | There is no need for the CSE to have access to CV's. they are not dealing with CV's. Please delete resume option for CSE |  | All CSE is going to be allocated to Individually Franchisee.
|  | Defining of the payment Milestones |  | CSE should have access to their own completed sales and pending sales on their Sales service section (on the drop down Sales please add the following options - completed sales and Pending Sales.
Initial payment deposit (via payment gatway thru the system)
Reports a) Order reports status b) Sales Statics (filters - days/ months/ years)
Notification a) When ever there is an update in payment b) Status update c) Announcement message from admin is received. d) A lead is shared by the franchise executive
|  | Settings |  |  | 2019-07-07
On the Dash board for (CSE) only have completed sales, Pending Sales, Team Memeber and a message portal.
2 | Franchise Executive | Login to the application via login details created by Super admin/Customer Support Admin | All user must have First Name, Surename, Gender and ID
|  | Setting up the profile (i.e. completing his/ her profile details) | Franchisee need's to be able to add or delete their own consultants
Viewing the CV requests/ sales lead request shared by customer support admin.
Ability to assign the sales lead to customer support executive of the particular loaction.
Ability to post a job
|  | Reports a) Cv's received status b) Cv's Statics (filters - days/ months/ years) like how many CV's shared with respect to particular filtered. c) Sales lead received status d) Action take with respect to each sales lead |  |  | 2019-07-19
Notification a) when ever a new Cv is received b) Announcement message from admin is received.
Settings
3 | End user | Ability to view the complete front end of the website.
Submit the CV or any service request via form on the website
Contact us form (which will be directly submitted to the Admin)
4 | Customer Support Admin | Login to the application via login details created by Super admin |  |  |  | CSA Dashboard - Only Include thefollowing Tabs ( 1 Customer service Admin 2 Franchise executive 3 Customer Support Executive 4 Employee (Users) 5 Sales Completed 6 Sales Pending 7 New Orders 8 Resume. Also add an option to send message to staff within the company, group or individual.
Ability to create logins for other users (Franchise Executive and Customer Support Executive) of the application.
|  | View Sales report w.r.t user/ location/ time period |  |  | 2019-06-28
View Cv's request w.r.t user/ location/ time period
Ability to create the customer support executive profile.
Ability to assign a sales lead/Job request (Cv received) to the particular franchise Executive w.r.t location
5 | Super- Admin | User management | Please make sure you have Order status that CSA can update as the order comes through. |  |  | Allow the supper adim to give full or limited access to CSA portal.
|  | Ability to create logins for other users of the application |  |  | 2019-06-26
View user w.r.t location
View sales report w.r.t filters user/location/time period
Access to complete master data of the application.
View messages received from the contact form and assigning it to a particular department if required.
Settings
Change Requirement
|  | Form Builder/create 12 indivisible form of according to service | Could you please add a 20% VAT to each order form ( so we can manually add 20% after selecting set-up cost and service charge) once the Vat is added then the total amount should be shown in a box |  | Done
|  | Show All forms of service/edit/update/ | Could you please add save order on the order form. (this can be used for the consultant to save information about the business if the sale is not 100%completed. |  | Done
|  | manage of all payment paid /pending of according to service | CSA - in view user i can see client as (User) Change the user to Client and also have client on seperate tab so they do not interfear with Employee.
recurring payment according to all user and service
Dashboard ending payment for client/sale exective/superadmin/franchise